## Schedule
Task ID | Task Name | Phase | Start Date | Finish Date | Duration (days) | % Complete | Predecessors | Resource | Baseline Start | Baseline Finish | Float (days)
T001 | Site Preparation & Excavation | Civil & Structure | 2024-06-01 | 2024-06-10 | 9 | 78 |  | MEP Team | 2024-06-01 | 2024-06-10 | 3
T002 | Foundation Work | Civil & Structure | 2024-06-09 | 2024-06-24 | 15 | 97 | T001 | Contractor A | 2024-06-09 | 2024-06-24 | 3
T003 | Structural Steel Erection | Civil & Structure | 2024-06-17 | 2024-06-27 | 10 | 80 | T002 | MEP Team | 2024-06-17 | 2024-06-27 | 5
T004 | Roof Installation | Civil & Structure | 2024-06-25 | 2024-07-04 | 9 | 97 | T003 | MEP Team | 2024-06-25 | 2024-07-04 | 1
T005 | Exterior Walls & Finish | Civil & Structure | 2024-07-03 | 2024-07-10 | 5 | 74 | T004 | Contractor B | 2024-07-03 | 2024-07-08 | 0
T006 | MV Power Distribution Installation | MEP Rough-In | 2024-07-11 | 2024-07-26 | 13 | 87 | T005 | Contractor B | 2024-07-11 | 2024-07-24 | 0
T007 | LV Electrical Panel Installation | MEP Rough-In | 2024-07-19 | 2024-08-01 | 10 | 89 | T006 | MEP Team | 2024-07-19 | 2024-07-29 | 0
T008 | Cable Routing & Conduit | MEP Rough-In | 2024-07-27 | 2024-08-16 | 13 | 93 | T007 | Contractor B | 2024-07-27 | 2024-08-09 | 0
T009 | Cooling Tower Installation | MEP Rough-In | 2024-08-04 | 2024-08-19 | 9 | 86 | T008 | MEP Team | 2024-08-04 | 2024-08-13 | 0
T010 | Chiller System Rough-In | MEP Rough-In | 2024-08-12 | 2024-08-25 | 13 | 76 | T009 | Electrical Team | 2024-08-12 | 2024-08-25 | 4
T011 | AHU Installation | MEP Rough-In | 2024-08-20 | 2024-09-01 | 12 | 97 | T010 | MEP Team | 2024-08-20 | 2024-09-01 | 1
T012 | Plumbing Rough-In | MEP Rough-In | 2024-08-28 | 2024-09-12 | 15 | 94 | T011 | Contractor B | 2024-08-28 | 2024-09-12 | 0
T013 | UPS System Installation (Batt 1) | Equipment Installation | 2024-09-05 | 2024-09-18 | 8 | 88 | T012 | Electrical Team | 2024-09-05 | 2024-09-13 | 0
T014 | UPS System Installation (Batt 2) | Equipment Installation | 2024-09-13 | 2024-09-26 | 13 | 94 | T013 | Contractor A | 2024-09-13 | 2024-09-26 | 0
T015 | Diesel Generator Set Installation | Equipment Installation | 2024-09-21 | 2024-09-28 | 7 | 97 | T014 | MEP Team | 2024-09-21 | 2024-09-28 | 3
T016 | Switchgear Installation | Equipment Installation | 2024-09-29 | 2024-10-09 | 10 | 92 |  | Electrical Team | 2024-09-29 | 2024-10-09 | 1
T017 | PDU Installation & Testing | Equipment Installation | 2024-10-07 | 2024-10-14 | 5 | 70 |  | Electrical Team | 2024-10-07 | 2024-10-12 | 0
T018 | Server Rack Installation | Equipment Installation | 2024-10-15 | 2024-10-23 | 8 | 85 |  | Contractor B | 2024-10-15 | 2024-10-23 | 5
T019 | Cooling Unit Final Installation | Equipment Installation | 2024-10-23 | 2024-11-07 | 15 | 80 |  | Contractor A | 2024-10-23 | 2024-11-07 | 2
T020 | Power System Testing | Commissioning Prep | 2024-10-31 | 2024-11-09 | 9 | 100 |  | Contractor A | 2024-10-31 | 2024-11-09 | 1
T021 | Cooling System Testing | Commissioning Prep | 2024-11-08 | 2024-11-22 | 7 | 71 | T020 | Contractor A | 2024-11-08 | 2024-11-15 | 0
T022 | Network Infrastructure Test | Commissioning Prep | 2024-11-16 | 2024-11-28 | 12 | 99 | T021 | Contractor A | 2024-11-16 | 2024-11-28 | 2
T023 | Fire Suppression Test | Commissioning Prep | 2024-11-24 | 2024-12-04 | 10 | 81 |  | Contractor B | 2024-11-24 | 2024-12-04 | 0
T024 | Security System Test | Commissioning Prep | 2024-12-02 | 2024-12-15 | 13 | 92 |  | Electrical Team | 2024-12-02 | 2024-12-15 | 0
T025 | Final Inspections | Commissioning Prep | 2024-12-10 | 2024-12-19 | 6 | 71 |  | Contractor A | 2024-12-10 | 2024-12-16 | 0
T026 | Punch List Resolution | Commissioning Prep | 2024-12-18 | 2024-12-30 | 12 | 85 |  | Contractor A | 2024-12-18 | 2024-12-30 | 3
T027 | Handover Documentation | Commissioning Prep | 2024-12-26 | 2025-01-10 | 9 | 92 | T026 | MEP Team | 2024-12-26 | 2025-01-04 | 0